PoolUp

Solo Dev Build Bible

Week-by-Week Guide from Zero to Launch

Version 2.0 — India Edition — April 2026

# The Solo Dev Manifesto

You are one person building a fintech product. Every decision must favour simplicity over elegance, shipping over perfection, and revenue over features. Follow these rules:

- Ship the CRON first. If the CRON doesn't work, nothing works. The payment engine is the product. Build it, test it, trust it.

- Use boring technology. Supabase + React Native + Razorpay. No custom backends. No Kubernetes. No microservices. You are one person.

- One feature at a time. Don't build the power-up store while the check-in camera is broken. Serial execution, not parallel.

- Test with real money early. Razorpay test mode from Week 5. Real money with 5 friends by Week 11. You cannot simulate payment edge cases.

- Cut scope ruthlessly. If a feature isn't in MVP, it doesn't exist. Write it down, forget it, build it later.

- WhatsApp is your marketing department. Every share card, every invite link, every win celebration is optimised for WhatsApp forwarding. This IS your growth strategy.

Your MVP Is: Auth + Pool Create/Join + Camera Check-in + CRON Fine Engine + Social Feed + Razorpay (UPI buy-in + Autopay fines + Route payouts) + Wallet + Push Notifications. That's it. Everything else is Phase 2+.

# Week 1: Project Setup & Auth

## Day 1–2: Project Bootstrap

- Create Expo project: npx create-expo-app poolup --template blank-typescript

- Install core dependencies: @supabase/supabase-js, react-native-razorpay, @tanstack/react-query, zustand, expo-camera, expo-image-manipulator, expo-notifications

- Set up folder structure (see LLD Section 4)

- Create Supabase project in Mumbai region (ap-south-1)

- Set up Git repo. Main branch = production. Dev branch = working.

## Day 3–4: Database Schema

- Write migration 001: Create all enum types

- Write migration 002: Create users, pools, pool_members, check_ins, transactions, reactions, pool_events tables

- Write migration 003: Create indexes (pool_members by pool_id+status, transactions by idempotency_key, check_ins by user+pool+date)

- Write migration 004: RLS policies for ALL tables

- Run migrations. Verify in Supabase Studio.

- Test RLS: try to read another user's transactions. Must fail.

Day 4 Checkpoint Database must be fully set up with all tables, constraints, indexes, and RLS policies. If this is not solid, everything built on top will be fragile. Spend the extra time.

## Day 5–7: Authentication

- Implement Supabase Auth with Phone OTP

- Set up MSG91 or Gupshup as SMS provider in Supabase dashboard

- Build LoginScreen: phone input + OTP input

- Build ProfileSetupScreen: name, username (check uniqueness), avatar upload

- Build auth store (Zustand): currentUser, isAuthenticated, session

- Build useAuth hook: login, verifyOTP, setupProfile, logout

- Add Google Sign-In and Apple Sign-In

- Test on physical device (OTP doesn't work in simulator)

Week 1 Deliverable User can sign up with phone OTP, set up profile, and see an empty home dashboard. Auth persists across app restarts. Database has all tables and RLS.

# Week 2: Pool Creation & Join

## Day 8–10: Pool Creation Flow

- Build CreatePool screen (4 steps): Name, Duration, Stakes, Review

- Implement form validation for all fields (buy-in ₹99–₹5,000, fine ₹25–₹500, duration 7–365)

- Generate 6-character alphanumeric invite code (check uniqueness)

- Insert pool row via Supabase client

- Build share screen: WhatsApp share button (using react-native-share), copy invite code, show QR

- Build deep link handling (Expo Linking) for pool invites

## Day 11–12: Pool Join Flow

- Build JoinPool screen: invite code input or deep link handler

- Implement full validation chain (code valid, pool pending, not full, not already member)

- Display pool rules + consent screen

- For now: skip payment (we add Razorpay in Week 5). Just insert pool_members row.

- Build home dashboard: pool cards showing name, pot, streak, days remaining

## Day 13–14: Pool Detail Screen

- Build PoolDetailScreen with sticky header (name, pot, days, members)

- Build member list with streaks and compliance

- Build basic leaderboard sort (streak DESC, fines ASC, compliance DESC, join_date ASC)

- Navigation: Home tab shows pool cards, tap card → Pool Detail

Week 2 Deliverable User can create a pool, share invite code via WhatsApp, join a pool via code, and see pool details with member list. No payments yet.

# Week 3: Check-in Engine & Feed

## Day 15–17: Camera Check-in

- Build CameraScreen using expo-camera: front/rear toggle, capture button

- NO gallery access. Camera only. This is anti-cheat by design.

- Implement liveness prompt (1-in-3 random): show overlay text on camera view

- Build PreviewScreen: full-screen photo, retake button, caption input (200 chars), submit button

- Implement client-side blur detection (calculate Laplacian variance of image)

- Implement image compression via expo-image-manipulator (target <500KB, JPEG 70%)

- Upload to Supabase Storage. Generate signed URL.

- Build Edge Function: generate-thumbnail (200x200) + watermark (timestamp overlay)

- Insert check_ins row. Return success.

- Build SuccessScreen: streak count, fire emoji, auto-navigate to feed

Compression is Critical Indian users have 10+ MP cameras on budget phones. A raw photo can be 5MB+. On patchy 4G, uploading 5MB takes 30+ seconds and often fails. Compress to <500KB BEFORE upload. This single optimisation will prevent 50% of check-in failures.

## Day 18–20: Social Feed

- Build FeedScreen: vertical scroll of today's check-ins

- Each card: avatar, name, caption, check-in image (thumbnail), timestamp, reaction bar

- Implement reactions: tap reaction icon to add/update. UNIQUE(check_in_id, user_id) in DB.

- Implement reaction counts on each card

- Set up Supabase Realtime subscription on check_ins table (pool_id filter)

- New check-ins appear in feed instantly without pull-to-refresh

## Day 21: Wall of Shame Events

- Build event cards in feed for pool_events (missed_day, fine_issued, streak_milestone)

- Style: red border for misses, fire border for milestones

- These will be populated by the CRON (built in Week 5–6), but build the UI now

Week 3 Deliverable User can take a photo check-in, see it in the pool feed, react to others' check-ins. Real-time updates work. No CRON or payments yet.

# Week 4: Wallet, Notifications & Polish

## Day 22–24: Wallet & Ledger

- Build WalletDashboard: active pool balances, lifetime stats

- Build TransactionLedger: list all transactions (date, type, amount, status, pool name)

- Tap transaction for details (Razorpay ID, UTR number — will be populated after Week 5)

- Build PaymentMethodsScreen: show UPI ID, saved cards (placeholder until Razorpay integration)

## Day 25–26: Push Notifications

- Set up expo-notifications. Request permission. Save push token to users table.

- Build Edge Function: send-reminders (check for members without check-in, send push 3h before deadline)

- Build notification center screen (list of past notifications)

- Implement quiet hours (10pm–7am IST): skip notifications during this window

## Day 27–28: Profile & Settings

- Build ProfileScreen: avatar, name, username, stats, badges (empty for now), pool history

- Build SettingsScreen: edit profile, notification preferences, language (EN/HI), logout, delete account

- Implement account deletion flow (soft-delete with OTP re-verification)

- Build bottom tab navigator: Home, Explore (placeholder), Wallet, Profile

Week 4 Deliverable App feels like a real product. All screens built. Navigation complete. Push notifications work. No real money yet.

Month 1 Complete You now have a functional app shell: auth, pools, check-ins, feed, wallet, notifications, profile. Everything works except the MONEY. Month 2 is all about the financial engine.

# Week 5–6: Razorpay Integration (The Hard Part)

This is the most difficult 2 weeks of the entire project. Plan 2 full weeks minimum. Do not rush this. Every payment edge case you skip now will become a production fire later.

## Week 5: UPI Autopay + Buy-in

### Day 29–30: Razorpay Setup

- Create Razorpay account (test mode). Get API keys.

- Store keys as Supabase Secrets (never in client code).

- Install react-native-razorpay in the Expo project.

- Build Edge Function: create-razorpay-customer (called on first pool join).

### Day 31–33: Buy-in Payment

- Build Edge Function: create-buy-in-order → creates Razorpay Order → returns order_id to client

- Client opens Razorpay Checkout with order_id. User pays via UPI/Card/Netbanking.

- Build Edge Function: payment-webhook → receives payment.captured → inserts deposit transaction → inserts pool_members row

- Handle payment.failed webhook: notify user, do not create member row

- Test with Razorpay test UPI ID (success@razorpay)

### Day 34–35: UPI Autopay Mandate

- Build Edge Function: create-mandate → creates Razorpay Subscription with UPI autopay registration

- Client triggers mandate approval in user's UPI app

- Webhook: subscription.authenticated → store mandate_id on pool_members

- Integrate into pool join flow: mandate BEFORE buy-in (mandate fails more often, fail early)

- Test: verify mandate appears in Razorpay dashboard

UPI Autopay Testing Razorpay test mode does not fully simulate UPI Autopay. You can test the API flow, but the actual UPI app approval step only works in live mode. Plan to do a real-money test in Week 11 with ₹99 buy-in.

## Week 6: CRON Fine Engine + Payouts

### Day 36–38: CRON Fine Engine

- Build Edge Function: process-checkins (the core CRON)

- Logic: for each active pool past deadline → for each active member → check for today's check-in

- If missing: check shield → check grace → create fine transaction with idempotency_key → charge via mandate

- Handle charge success: update transaction, recalculate pot (SUM, never increment), write pool_event

- Handle charge failure: set status=failed, log failure_reason, schedule retry

- Set up pg_cron to invoke this function every minute

- Set up Cronitor or Healthchecks.io for heartbeat monitoring

- TEST EXTENSIVELY: create a test pool with 2 members, set deadline to 5 minutes from now, verify the entire flow

### Day 39–40: Retry Logic

- Build Edge Function: process-retries

- Find transactions with status=failed and retry_count < 3

- Retry schedule: 6h, 24h, 72h after initial failure

- On retry success: update status, update pot

- On retry 3 failure: set member status=delinquent, write off fine from pot

- Send notifications at each retry attempt

### Day 41–42: Payout Engine

- Build Edge Function: process-payout

- Triggered when CRON detects pool end_date passed

- Calculate standings per payout_rule (winner_takes_all first, others in Phase 2)

- Deduct platform fee (5%). Calculate GST (18% of fee).

- Create Razorpay Fund Account for winner (linked to their UPI ID)

- Create Razorpay Route Transfer from platform balance to fund account

- Handle transfer.processed webhook: update payout transaction, notify winner

- Test: complete a test pool manually. Verify payout arrives in UPI.

Week 6 Deliverable COMPLETE FINANCIAL ENGINE WORKING IN TEST MODE. Buy-in → Mandate → CRON detects miss → Auto-charges fine → Pool completes → Payout to winner. This is the product.

# Week 7–8: Pre-debit Notifications, Edge Cases & Hardening

## Week 7: RBI Compliance + Edge Cases

- Day 43–44: Pre-debit notifications. Build Edge Function that sends notification 24h before each potential auto-debit. This is an RBI requirement, not optional.

- Day 45: Manual pay fallback. When UPI autopay fails, show 'Pay Now' button that opens Razorpay Checkout for manual payment. On success: update fine transaction.

- Day 46: Pool activation logic. CRON checks pending pools past start_date. If ≥2 members: activate. If <2: cancel + refund.

- Day 47: Pool completion + auto-complete. When only 1 active member remains: auto-complete pool. Sole survivor gets net pot.

- Day 48–49: Refund flow. Pool cancelled before start: refund all buy-ins via Razorpay Refund API. No platform fee.

## Week 8: Testing & Polish

- Day 50–51: End-to-end testing. Create 3 test pools with different settings. Manually test every flow: join, check-in, miss, fine, retry, payout, refund.

- Day 52: Idempotency testing. Run CRON twice in same minute. Verify no double charges. Kill CRON mid-execution. Verify recovery.

- Day 53: Error handling. Test every failure: Razorpay down, Supabase down, network timeout, image upload fail, mandate revoked.

- Day 54: UI polish. Loading states, error toasts, empty states, pull-to-refresh, skeleton screens.

- Day 55–56: Performance. Test on a ₹8,000 phone (Redmi Note). Profile app startup. Optimise image loading (use thumbnails in feed).

Week 8 Deliverable Rock-solid app working end-to-end in Razorpay test mode. All financial flows tested. Edge cases handled. Ready for real money.

# Week 9–10: Legal, Real Money & Closed Beta

## Week 9: Legal & Compliance

- Day 57–58: Legal documents. Write Terms of Service, Privacy Policy (DPDP Act compliant), Consent Copy for auto-charging. Have a lawyer review.

- Day 59: Consent screen. Integrate lawyer-approved consent text into pool join flow. Must explicitly state auto-debit authorisation.

- Day 60: GST setup. Register for GST (if not already). Implement GST calculation on platform fees. Auto-generate GST invoices.

- Day 61: Razorpay go-live. Switch Razorpay to live mode. Submit platform details for Razorpay review. This can take 3–5 business days.

- Day 62–63: App Store prep. Screenshots, app description, privacy policy links. Category: Health & Fitness. Emphasise accountability, not money.

## Week 10: Closed Beta with Real Money

- Day 64: Recruit beta group. 10–20 friends/family. 3–5 pools. ₹99 buy-in (lowest tier). Real money. Real UPI.

- Day 65–70: Monitor everything. Watch CRON runs, payment success rates, UPI mandate approvals. Fix bugs as they appear. Talk to testers daily.

- Day 67: WhatsApp templates. Submit WhatsApp Business API message templates for approval (5–7 day Meta review). Need templates for: fine alert, payout notification, reminder.

Week 10 is Make-or-Break This is where you discover all the edge cases you didn't think of. UPI apps behave differently (GPay vs PhonePe vs Paytm). Banks have different autopay support levels. Some users will have trouble setting up mandates. Take notes on every issue. Fix the critical ones before launch.

Week 10 Deliverable 5+ real-money pools completed successfully. At least one full payout cycle confirmed. Major bugs fixed. Legal documents in place.

# Week 11–12: Launch

## Week 11: Final Prep

- Submit to Google Play Store (3–7 day review for real-money apps)

- Submit to Apple App Store (1–3 day review if positioned correctly)

- Set up analytics: Mixpanel or CleverTap. Track all funnel events.

- Set up error monitoring: Sentry for crash reports.

- Set up financial monitoring: daily Razorpay reconciliation check.

- Prepare launch WhatsApp messages and share cards.

## Week 12: Soft Launch

- Launch to waitlist / early access group (200–500 users)

- Monitor daily: CRON health, payment success rate, check-in rate, user feedback

- Respond to every user issue within 2 hours (you are support now)

- Fix critical bugs immediately. Non-critical bugs go to backlog.

- Start collecting data for North Star metrics (see Analytics doc)

LAUNCH COMPLETE You have a live product with real users and real money. Congratulations. Now the real work begins.

# Post-Launch: Phase 2–6 Priorities

## Phase 2: Engagement (Month 2–3)

| Week | Feature | Why Now |
| --- | --- | --- |
| 13–14 | XP + Levelling system | Retention hook. Users see progress. |
| 14–15 | Badge system (first 5 badges) | Social proof. Profile feels alive. |
| 15–16 | PoolUp Pro subscription (₹199/mo) | Revenue diversification. Pro badge = status. |
| 16–17 | WhatsApp Business API integration | Higher open rates than push. Financial alerts on WhatsApp. |
| 17–18 | Share cards (check-in, milestone, win) | Viral growth. Every share is a marketing impression. |

## Phase 3: Growth (Month 3–4)

| Week | Feature | Why Now |
| --- | --- | --- |
| 19–20 | Public pools + Explore tab | Organic discovery. Non-invite growth. |
| 20–21 | Spectator mode | Low-friction entry. Watch → try → pay funnel. |
| 21–22 | Comments (threaded, 3 levels) | Social stickiness. Trash talk = engagement. |
| 22–24 | Power-up store (Shield, Alarm Bomb, Streak Freeze) | Revenue + fun. Shield is pure margin. |

## Phase 4: Creator (Month 4–5)

| Week | Feature | Why Now |
| --- | --- | --- |
| 25–26 | Creator verification + dashboard | Onboard first 10 creators. |
| 26–28 | Creator pools with revenue share | Each creator is an acquisition channel. |
| 28–30 | Hindi language support | Unlocks Tier 2 cities and 2x addressable market. |

## Phase 5: Scale (Month 5–6)

| Week | Feature | Why Now |
| --- | --- | --- |
| 31–32 | Seasons (90-day cycles) | Retention loops. Re-engagement of lapsed users. |
| 33–34 | Strava + Google Fit integration | Auto-verification for run/step challenges. |
| 35–36 | Sponsored challenges pilot | First brand deal. Revenue validation. |

# Tools, Services & Monthly Costs

| Service | Free Tier | Paid Tier (When Needed) | Est. Monthly Cost |
| --- | --- | --- | --- |
| Supabase | 500MB DB, 1GB storage, 50K MAU | Pro: 8GB DB, 100GB storage | ₹1,500 (from Month 3) |
| Razorpay | No monthly fee. 2% per transaction. | — | 2% of GMV |
| Expo / EAS | Free builds + updates | Production: priority builds | ₹2,400 (from launch) |
| MSG91 (SMS OTP) | Free tier available | Pay per SMS (₹0.20/SMS) | ₹1,000–₹5,000 |
| Gupshup (WhatsApp API) | — | ₹0.50–₹1.00 per message | ₹2,000–₹10,000 |
| Cronitor | Free (5 monitors) | Pro if needed | ₹0 (free tier) |
| Sentry (error monitoring) | Free (5K events/mo) | Team plan | ₹0 (free tier) |
| Mixpanel (analytics) | Free (20M events/mo) | — | ₹0 (free tier) |
| Domain + hosting | — | Cloudflare + domain | ₹500 |
| Apple Developer Account | — | Annual fee | ₹8,500/year |
| Google Play Console | — | One-time fee | ₹2,000 (one-time) |

Total Monthly Cost (Pre-Revenue) ~₹5,000–₹8,000/month until you have paying users. After 1,000 active pools: Razorpay fees (~₹15,000) + Supabase Pro (~₹1,500) + WhatsApp (~₹5,000) = ~₹21,500/month against ~₹2.6 lakh/month revenue. Profitable from early scale.

# Recommended Daily Routine (Solo Dev)

| Time (IST) | Activity | Duration |
| --- | --- | --- |
| 7:00–8:00 | Review CRON logs, Razorpay dashboard, error reports | 1 hour |
| 8:00–12:00 | Deep work: build features (no meetings, no Slack, no Twitter) | 4 hours |
| 12:00–13:00 | Lunch + respond to user feedback / bug reports | 1 hour |
| 13:00–17:00 | Deep work: continue features or fix bugs | 4 hours |
| 17:00–18:00 | Test today's work on physical device. Write tomorrow's task list. | 1 hour |
| Evening | Respond to beta testers on WhatsApp. Plan tomorrow. | 30 min |

The 10-Hour Rule You have ~10 productive hours per day as a solo dev. Protect them ruthlessly. No feature requests from friends. No 'quick fixes' that take 3 hours. No redesigning the logo. Code, test, ship. Repeat.

━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━━

Pehle CRON banao. Phir Razorpay lagao. Phir maza aayega.

(Build the CRON first. Then plug in Razorpay. Then the fun begins.)

Good luck. Ship fast. Charge real money. 🚀